## Trang tính1
STT | Name | Duration (days) | Start | Finish | Responsible | Progress | Notes
1 | Fitness Course Management |  | 27/09/2024 09:30
2 | Project Start | 4 | 27/09/2024 09:30
3 | Preparation | 4 | 27/09/2024 09:30 | 2024-01-10 22:00 | All | 100%
3.1 | Designing a diagram | 4 | 27/09/2024 09:30 | 2024-01-10 13:00 | All | 100% | Minh, Duyen, Huy : creating their own diagram and then combining to create a complete diagram. They have done these tasks which assigned by Minh. Khang, Dat : Not doing these tasks (causeless), but having their own ideas when matching diagram. Diagram: https://drive.google.com/file/d/1ytzVqHMEek7cAJG8Nthq8oWRanF-G7Pw/view?usp=sharing
3.2 | Assigning task | 0 | 2024-01-10 17:00 | 2024-01-10 22:00 | Minh | 100% | Tasks were assigned for each member to code each part, which is designed in our diagrams.
4 | Implement |  | 2024-02-10 07:00 | 2024-01-11 09:15
4.1 | Database in SQL Server | 2 | 2/10/2024 13:00:00 AM | 2024-04-10 13:00 | Minh | 100%
4.2 | Research information about other source related to Fitness Course | 1 | 2024-02-10 10:00 | 2024-02-10 12:00 | Huy, Duyên | 100%
4.3 | Implement code: Nutrition, PracticalDay, PracticalDaySerivce, NutritionRepository, PracticalDayRepository, Workout, WorkoutService, WorkoutRepository | 26 | 2024-03-10 | 28/10/2024 0:00 | Khang | 80%
[5 empty] | Minh | 20%
4.4 | Implement code: Coach, User, CoachService, UserService, CoachRepository, UserRepository | 26 | 2024-03-10 | 28/10/2024 0:00 | Dat | 80%
[5 empty] | Minh | 20%
4.5 | Implement code: Course, CourseCombo, RegistedCourse, CourseService, CourseComboService, RegistedCourseService | 26 | 2024-03-10 | 28/10/2024 0:00 | Huy | 80%
[5 empty] | Minh | 20%
4.6 | Implement code: Schedule,UserProgress, ScheduleService, UserProgressService, ScheduleRepository, UserProgressRepository | 26 | 2024-03-10 | 28/10/2024 0:00 | Duyên | 80%
[5 empty] | Minh | 20%
4.7 | Implement code: Exception package, Utils package, SQLServerConnection, FitnessCourseManagement, Menu, Create database in SQL Server, NotificationService | 9 | 20/10/2024 0:00 | 28/10/2024 0:00 | Minh | 100%
5 | Two Check | 2 | 29/10/2024 00:00 | 2024-01-11 01:00 | Minh | 100%
6 | Finish project |  |  | 2024-01-11 07:00 | All | 100%